## Portal
Area | Issue | Status
Supplier Account registration and Supplier Profile Completion | 1. Confirm that suppliers can be registered per region | Pending
| 2. Supplier profile completion should be automated | Pending
| 3. Created suppliers should be added to supplier table before vendor table | Pending
| 4. System should not allow processing before mandatory documents are attached | Pending
| 5. Allow for capture of document expiry | Pending
| 6. Integration with EDMS missing | Pending
| 7. Have an approval for supplier registration process | Done
Supplier Prequalification | 1. View invitations prior to login. | Pending
| 2. Trouble setting date using calendar date picker | Pending
| 3. Add dropdown list of bank codes | Pending
| 4. have profile summary before submission | Pending
| 5. Have special requirements for categories listed on portal before applying | Pending
| 6. Have list of regions when responding to prequalification | Pending
| 7. Documents upload during pre-qualification response not working | Pending
| 8. submit prequalification error | Pending
| 9. Have email notification sent out to successful and unsuccessful suppliers. | Pending | Nav
| 1. RC on header should pick on lines automatically | Pending | Nav
| 2. To show case how different regions will be handled | Pending | Nav
| 5. When a user clicks apply to take them to the login page and on login redirect to the specific request for response | Pending
| 6. To have RFP lines mapped automatically to Request RC | Pending | Nav
| 7. Documents attached on portal to only show based on list on NAV | Pending
| 8.Ensure system validates before submiting | Pending
| 9. System to automatically close based on dates | Pending
Responding to a RFS(As per the Different tender methods) | 1. Add unit available when responding to RFQ | Pending
| 2. Unit cost should not auto populate | Pending
| 3. Make quantity field read only | Pending
| 4. change button status to applied after submission. | Pending
| 5. Add a download feature to access tender documents | Pending